## Sheet1
PROJECT TITLE | PRICE PREDICTION OF AIRBNB - GROUP 6
|  | PROJECT START: | 2023-01-09
|  | DISPLAY WEEK: | 8
[5 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22
 | time axis 2023-02-27 to 2023-05-28
TASK | ASSIGNED TO | PROGRESS | START DATE | END DATE | time axis 2023-02-27 to 2023-05-28
PHASE 1:PLANNING
Ideation and research | all members | 100% | 2023-01-10 | 2023-01-11
dataset approval | all members | 100% | 2023-01-12 | 2023-01-16
collecting and developing the dataset | joyal patel | 100% | 2023-01-17 | 2023-01-19
business problem analysis | Harshkumar Dineshbhai Patel | 100% | 2023-01-20 | 2023-01-28
identify the factors | Ezekiel Ayeni | 100% | 2023-01-29 | 2023-01-31
PHASE 2:CLEANING
data merging | Jyoti bala | 100% | 2023-02-01 | 2023-02-06 | bar: 2023-03-22 to 2023-03-25
dataset cleaning | Harshkumar Dineshbhai Patel and joyal patel | 100% | 2023-02-07 | 2023-02-11
dataset analysis and project planner | Raihaanah and Ezekiel Ayeni | 100% | 2023-02-12 | 2023-02-19
PHASE 3:PROJECT DEVELOPING
EXPLORATORY DATA ANALYSIS | Jyoti bala | 80% | 2023-02-20 | 2023-02-28
LOGICAL ANALYSIS | Harshkumar Dineshbhai Patel and joyal patel | 25% | 2023-03-01 | 2023-03-05
EXCEL ANALYSIS | all members |  | 2023-03-06 | 2023-03-10
TABLEAU | Raihaanah and Ezekiel Ayeni |  | 2023-03-11 | 2023-03-18
DASHBOARD CREATING | Jyoti bala |  | 2023-03-19 | 2023-03-25
PHASE 4:REPORT MAKING
PRESENTATION | EZekiel Ayeni |  | 2023-03-26 | 2023-04-02
REPORT | Jyoti bala and Raihaanah |  | 2023-04-03 | 2023-04-09